## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Period Highlight: | 10 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [6 empty] | % Complete (beyond plan)
ACTIVITY | MEMBER | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (September - October) | [20 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
[7 empty] | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37
Code: class for argument passing | Ishikawa | 10 | 6 | 10 | 6 | 0%
Code: class for user memory access | Javier | 10 | 6 | 10 | 6 | 0%
Code: system call infrastracture | Yang | 10 | 6 | 10 | 6 | 0%
Debug: argument passing | Yang | 16 | 6 | 16 | 6 | 0%
Debug: user memory access | Ishikawa | 16 | 6 | 16 | 6 | 0%
Debug: system call infrastracture | Javier | 16 | 6 | 16 | 6 | 0%
Changelog: argument passing | Yang | 22 | 2 | 22 | 2 | 0%
Changelog: user memory access | Ishikawa | 22 | 2 | 22 | 2 | 0%
Changelog: system call infrastracture | Javier | 22 | 2 | 22 | 2 | 0%
Code: exit system call | Ishikawa | 24 | 6 | 24 | 6 | 0%
Code: write system call | Yang | 24 | 6 | 24 | 6 | 0%
Code: infinite loop for process_wait() | Javier | 24 | 6 | 24 | 6 | 0%
Debug: exit system call | Javier | 30 | 6 | 30 | 6 | 0%
Debug: write system call | Ishikawa | 30 | 6 | 30 | 6 | 0%
Debug: infinite loop for process_wait | Yang | 30 | 6 | 30 | 6 | 0%
Changelog: exit system call | Javier | 36 | 2 | 36 | 2 | 0%
Changelog: write system call | Ishikawa | 36 | 2 | 36 | 2 | 0%
Changelog: infinite loop for process_wait | Yang | 36 | 2 | 36 | 2 | 0%